## Agile Sprint Gantt
⚡ AGILE SPRINT GANTT CHART TEMPLATE FOR EXCEL
🗓 Edit yellow cells (Start, End, Story Points, Status) to update the Gantt automatically. Insert rows within a sprint block to add stories. Change project start date in C4.
Project: | Platform Rebuild | Team: | Rocket 🚀 | Scrum Master: | Andreea Rivera | Velocity: | 40 | (pts/sprint)
Project Start: |  | 2026-03-05 |  | Sprint Length (weeks): |  | 2 | weeks
# | Epic / Story / Task | Type | Start | End | Owner | Points | Status | Sprint | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
🚀 RELEASE 1.0 — Foundation & Core Auth
◼ Sprint 1
1 | Epic: User Authentication | EPIC | 2026-03-05 | 2026-03-19 | Team | 8 | ▶ Active | S1 | Auth module
2 | ✦ Set up project repo & CI/CD pipeline | STORY | 2026-03-05 | 2026-03-10 | Dev: Tina | 3 | ✔ Done | S1 | GitHub Actions
3 | ✦ Design login / signup UI screens | STORY | 2026-03-06 | 2026-03-12 | Des: Sam | 2 | ✔ Done | S1 | Figma
4 | ✦ Implement JWT auth backend | STORY | 2026-03-08 | 2026-03-16 | Dev: Alex | 5 | ✔ Done | S1 | Node.js
5 | ✦ Write auth unit tests | STORY | 2026-03-12 | 2026-03-17 | Dev: Tina | 2 | ✔ Done | S1 | Jest
6 | ◆ Sprint 1 Review & Retro | ◆ MILE | 2026-03-18 | 2026-03-18 | Scrum Master |  | — | S1
◼ Sprint 2
7 | Epic: User Profiles & Roles | EPIC | 2026-03-19 | 2026-04-02 | Team | 10 | ◌ To Do | S2
8 | ✦ User profile CRUD endpoints | STORY | 2026-03-19 | 2026-03-25 | Dev: Alex | 3 | ◌ To Do | S2 | REST API
9 | ✦ Role-based access control (RBAC) | STORY | 2026-03-21 | 2026-03-29 | Dev: Tina | 5 | ◌ To Do | S2
10 | ✦ Profile page frontend | STORY | 2026-03-23 | 2026-03-29 | Des: Sam | 3 | ◌ To Do | S2 | React
11 | ✦ Email verification flow | STORY | 2026-03-25 | 2026-03-30 | Dev: Alex | 2 | ◌ To Do | S2 | SendGrid
12 | ◆ Sprint 2 Review & Retro | ◆ MILE | 2026-04-01 | 2026-04-01 | Scrum Master |  | — | S2
◼ Sprint 3
13 | Epic: Dashboard & Analytics MVP | EPIC | 2026-04-02 | 2026-04-16 | Team | 12 | ◌ To Do | S3
14 | ✦ Data model & seed scripts | STORY | 2026-04-02 | 2026-04-07 | Dev: Tina | 3 | ◌ To Do | S3 | PostgreSQL
15 | ✦ Dashboard layout & charts | STORY | 2026-04-04 | 2026-04-12 | Des: Sam | 5 | ◌ To Do | S3 | Chart.js
16 | ✦ Real-time metric endpoints | STORY | 2026-04-06 | 2026-04-13 | Dev: Alex | 5 | ◌ To Do | S3 | WebSocket
17 | 🐛 Fix: Profile picture upload crash | 🐛 BUG | 2026-04-07 | 2026-04-09 | Dev: Tina | 1 | ◌ To Do | S3 | Hotfix
18 | ✦ Export to CSV feature | STORY | 2026-04-09 | 2026-04-13 | Dev: Alex | 3 | ◌ To Do | S3
19 | ◆ Sprint 3 Review & Retro | ◆ MILE | 2026-04-15 | 2026-04-15 | Scrum Master |  | — | S3
🚀 RELEASE 1.0 Launch 🎉
🔮 RELEASE 2.0 — Collaboration Features
◼ Sprint 4
20 | Epic: Team Workspaces | EPIC | 2026-04-16 | 2026-05-02 | Team | 13 | ◌ To Do | S4
21 | ✦ Workspace create / invite flow | STORY | 2026-04-16 | 2026-04-23 | Des: Sam | 3 | ◌ To Do | S4
22 | ✦ Workspace settings & permissions | STORY | 2026-04-18 | 2026-04-26 | Dev: Tina | 5 | ◌ To Do | S4
23 | ✦ Activity feed | STORY | 2026-04-20 | 2026-04-26 | Dev: Alex | 3 | ◌ To Do | S4
24 | ✦ Notifications (in-app + email) | STORY | 2026-04-22 | 2026-04-27 | Dev: Tina | 3 | ◌ To Do | S4
25 | ◆ Sprint 4 Review & Retro | ◆ MILE | 2026-05-01 | 2026-05-01 | Scrum Master |  | — | S4
◼ Sprint 5
26 | Epic: Real-time Collaboration | EPIC | 2026-05-02 | 2026-05-16 | Team | 15 | ◌ To Do | S5
27 | ✦ Live cursor & presence indicators | STORY | 2026-05-02 | 2026-05-09 | Dev: Alex | 5 | ◌ To Do | S5 | Socket.io
28 | ✦ Commenting & @mentions | STORY | 2026-05-04 | 2026-05-12 | Des: Sam | 5 | ◌ To Do | S5
29 | ✦ Version history / audit log | STORY | 2026-05-06 | 2026-05-12 | Dev: Tina | 5 | ◌ To Do | S5
30 | 🐛 Fix: Workspace invite email delay | 🐛 BUG | 2026-05-07 | 2026-05-09 | Dev: Alex | 1 | ◌ To Do | S5
31 | ◆ Sprint 5 Review & Retro | ◆ MILE | 2026-05-15 | 2026-05-15 | Scrum Master |  | — | S5
◼ Sprint 6
32 | Epic: Mobile Responsive & PWA | EPIC | 2026-05-16 | 2026-05-30 | Team | 10 | ◌ To Do | S6
33 | ✦ Responsive layout overhaul | STORY | 2026-05-16 | 2026-05-24 | Des: Sam | 5 | ◌ To Do | S6 | Tailwind
34 | ✦ PWA manifest & service worker | STORY | 2026-05-18 | 2026-05-24 | Dev: Tina | 3 | ◌ To Do | S6
35 | ✦ Offline mode with sync queue | STORY | 2026-05-20 | 2026-05-28 | Dev: Alex | 5 | ◌ To Do | S6 | IndexedDB
36 | ✦ Push notifications | STORY | 2026-05-22 | 2026-05-27 | Dev: Tina | 3 | ◌ To Do | S6
37 | ◆ Sprint 6 Review & Retro | ◆ MILE | 2026-05-29 | 2026-05-29 | Scrum Master |  | — | S6
🔮 RELEASE 2.0 Launch 🎉
LEGEND
| Done |  | Active |  | To Do |  | Bug / Hotfix |  | Milestone |  | Current Week
[10 empty] | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-09 | 2026-07-16 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-13 | 2026-08-20 | 2026-08-27
Formulas:
Status = IF([Velocity:]="","—",IF([Rocket 🚀]="","◌ To Do",IF(AND(ISNUMBER([Rocket 🚀]),[Rocket 🚀]<=TODAY(),[Scrum Master:]<=TODAY()),"✔ Done",IF(AND(ISNUMBER([Rocket 🚀]),[Rocket 🚀]<=TODAY()),"▶ Active","◌ To Do"))))