## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
Business Impact Analysis
Recovery
Strategies
Plan
Development
Testing & Exercise
Week 1
3
5
7
6 days
Develop Questionnaire
Send out questionnaire
5 days
Receive forms
5 days
Review forms
4 days
Follow-up interviews
10 days
Document requirements
3 days
Conduct gap analysis
5 days
Explore recovery strategies
6.6 days
Implement recovery strategy
8 days
Develop plan framework
4 days
Relocation Plans
5 days
IT disaster recovery plan
7 days
Document procedures
10 days
Requirements discovery
7 days
Document test results
4 days
Update BC plan
7 days
Training
9
11
13
2025
Organize recovery teams
25 days
Testing
Training for BC team
Orientation exercises
Management approval
Instructional Workshop
Management approval
Team roles
Incident Commander:
Adele Goodwin
HR/PR Officer:
Sheila Major
Information Technology:
Liam Benitez
Finance/Admin:
Violet Horton
Legal/Contracts:
Erik Mullen
Business Continuity Plan
Key activities and planning for risk mitigation