## Construction project Gantt
🏗 CONSTRUCTION PROJECT GANTT CHART TEMPLATE FOR EXCEL
Edit yellow cells (Start, End, % Complete) to update the chart automatically. Insert rows between task rows to add new tasks.
# | Phase / Task | Start | End | Days | Lead | % Done | Status | Notes | Jan '26 |  |  |  | Feb '26 |  |  |  | Mar '26 |  |  |  |  | Apr '26 |  |  |  | May '26 |  |  |  | Jun '26 |  |  |  |  | Jul '26 |  |  |  | Aug '26 |  |  |  |  | Sep '26 |  |  |  | Oct '26 |  |  |  | Nov '26 |  |  |  |  | Dec '26
▼ Task List | [8 empty] | 5/1 | 12/1 | 19/1 | 26/1 | 2/2 | 9/2 | 16/2 | 23/2 | 2/3 | 9/3 | 16/3 | 23/3 | 30/3 | 6/4 | 13/4 | 20/4 | 27/4 | 4/5 | 11/5 | 18/5 | 25/5 | 1/6 | 8/6 | 15/6 | 22/6 | 29/6 | 6/7 | 13/7 | 20/7 | 27/7 | 3/8 | 10/8 | 17/8 | 24/8 | 31/8 | 7/9 | 14/9 | 21/9 | 28/9 | 5/10 | 12/10 | 19/10 | 26/10 | 2/11 | 9/11 | 16/11 | 23/11 | 30/11 | 7/12 | 14/12 | 21/12 | 28/12
PHASE 1 — PRE-CONSTRUCTION & PERMITTING
1 | Site Survey & Soil Investigation | 2026-01-05 | 2026-01-19 | 14 | Civil Engineer | 100% | ✔ Complete
2 | Environmental Impact Assessment | 2026-01-10 | 2026-01-20 | 10 | Env. Consultant | 100% | ✔ Complete
3 | Architectural Design & Drawings | 2026-01-15 | 2026-02-12 | 28 | Lead Architect | 100% | ✔ Complete
4 | Structural Engineering Plans | 2026-01-25 | 2026-02-15 | 21 | Structural Eng. | 90% | ▶ In Progress
5 | Building Permit Application | 2026-02-12 | 2026-02-19 | 7 | Project Manager | 100% | ✔ Complete
6 | ◆ Permit Approval | 2026-02-19 | 2026-02-19 | 0 | Project Manager | 100% | ✔ Complete
PHASE 2 — SITE PREPARATION
7 | Demolition & Clearing | 2026-02-20 | 2026-02-27 | 7 | Demo Crew | 100% | ✔ Complete
8 | Temporary Site Utilities | 2026-02-20 | 2026-02-25 | 5 | Site Superintendent | 100% | ✔ Complete
9 | Erosion Control & Site Fencing | 2026-02-21 | 2026-02-25 | 4 | Site Crew | 100% | ✔ Complete
10 | Rough Grading & Earthworks | 2026-02-27 | 2026-03-09 | 10 | Grading Contractor | 95% | ▶ In Progress
11 | Underground Utilities Rough-In | 2026-03-06 | 2026-03-20 | 14 | Utility Contractor | 0% | ⚠ Overdue
PHASE 3 — FOUNDATION
12 | Excavation | 2026-03-20 | 2026-03-28 | 8 | Excavation Co. | 100% | ✔ Complete
13 | Footings & Foundation Walls | 2026-03-28 | 2026-04-09 | 12 | Concrete Crew | 90% | ▶ In Progress
14 | Waterproofing & Drainage Board | 2026-04-09 | 2026-04-15 | 6 | Waterproofing Sub | 75% | ▶ In Progress
15 | Backfill & Compaction | 2026-04-09 | 2026-04-15 | 6 | Site Crew | 60% | ▶ In Progress
16 | ◆ Foundation Inspection Passed | 2026-04-20 | 2026-04-20 | 0 | Inspector | 100% | ✔ Complete
PHASE 4 — STRUCTURAL FRAMING
17 | Steel Erection / Structural Frame | 2026-04-21 | 2026-05-12 | 21 | Steel Erector | 55% | ▶ In Progress
18 | Concrete Decks & Slabs | 2026-05-05 | 2026-05-19 | 14 | Concrete Crew | 30% | ▶ In Progress
19 | Roof Structure & Sheathing | 2026-05-19 | 2026-05-29 | 10 | Framing Crew | 10% | ▶ In Progress
20 | Exterior Sheathing & Weather Wrap | 2026-05-26 | 2026-06-03 | 8 | Framing Crew | 0% | ◌ Pending
PHASE 5 — BUILDING ENVELOPE
21 | Roofing Installation | 2026-05-29 | 2026-06-08 | 10 | Roofing Sub | 0% | ◌ Pending
22 | Exterior Cladding & Masonry | 2026-06-02 | 2026-06-20 | 18 | Masonry Sub | 0% | ◌ Pending
23 | Window & Curtain Wall Installation | 2026-06-12 | 2026-06-22 | 10 | Glazing Sub | 0% | ◌ Pending
24 | Exterior Caulking & Sealing | 2026-06-22 | 2026-06-29 | 7 | Paint Sub | 0% | ◌ Pending
PHASE 6 — MEP ROUGH-IN
25 | Mechanical (HVAC) Rough-In | 2026-06-04 | 2026-06-25 | 21 | Mech. Contractor | 0% | ◌ Pending
26 | Electrical Rough-In | 2026-06-04 | 2026-06-25 | 21 | Electrical Sub | 0% | ◌ Pending
27 | Plumbing Rough-In | 2026-06-04 | 2026-06-22 | 18 | Plumbing Sub | 0% | ◌ Pending
28 | Fire Suppression Rough-In | 2026-06-09 | 2026-06-23 | 14 | Fire Protection Sub | 0% | ◌ Pending
29 | ◆ MEP Rough-In Inspection | 2026-06-26 | 2026-06-26 | 0 | Inspector | 0% | ◌ Pending
PHASE 7 — INTERIOR FINISHES
30 | Insulation | 2026-06-27 | 2026-07-05 | 8 | Insulation Sub | 0% | ◌ Pending
31 | Drywall Hang & Finish | 2026-07-05 | 2026-07-19 | 14 | Drywall Sub | 0% | ◌ Pending
32 | Interior Painting | 2026-07-19 | 2026-07-29 | 10 | Paint Sub | 0% | ◌ Pending
33 | Flooring Installation | 2026-07-26 | 2026-08-07 | 12 | Flooring Sub | 0% | ◌ Pending
34 | Millwork, Cabinetry & Trim | 2026-08-03 | 2026-08-17 | 14 | Millwork Sub | 0% | ◌ Pending
35 | Doors, Hardware & Specialties | 2026-08-14 | 2026-08-21 | 7 | Finish Crew | 0% | ◌ Pending
PHASE 8 — MEP FINISHES & COMMISSIONING
36 | Mechanical Finishes & Balancing | 2026-08-03 | 2026-08-17 | 14 | Mech. Contractor | 0% | ◌ Pending
37 | Electrical Finishes & Panel Test | 2026-08-03 | 2026-08-15 | 12 | Electrical Sub | 0% | ◌ Pending
38 | Plumbing Fixtures & Pressure Test | 2026-08-07 | 2026-08-17 | 10 | Plumbing Sub | 0% | ◌ Pending
39 | Building Systems Commissioning | 2026-08-17 | 2026-08-24 | 7 | Commissioning Spec. | 0% | ◌ Pending
PHASE 9 — SITE WORK & LANDSCAPING
40 | Parking Lot & Paving | 2026-08-13 | 2026-08-23 | 10 | Paving Sub | 0% | ◌ Pending
41 | Sidewalks & Hardscape | 2026-08-21 | 2026-08-29 | 8 | Concrete Crew | 0% | ◌ Pending
42 | Landscaping & Irrigation | 2026-08-25 | 2026-09-04 | 10 | Landscape Sub | 0% | ◌ Pending
43 | Exterior Lighting | 2026-08-29 | 2026-09-03 | 5 | Electrical Sub | 0% | ◌ Pending
PHASE 10 — PROJECT CLOSEOUT
44 | Punch List Walk-Through | 2026-09-04 | 2026-09-09 | 5 | Project Manager | 0% | ◌ Pending
45 | Punch List Corrections | 2026-09-09 | 2026-09-16 | 7 | All Subcontractors | 0% | ◌ Pending
46 | Final Inspections & CO Application | 2026-09-20 | 2026-09-24 | 4 | Project Manager | 0% | ◌ Pending
47 | ◆ Certificate of Occupancy Issued | 2026-09-21 | 2026-09-21 | 0 | Project Manager | 0% | ◌ Pending
48 | Owner Handover & Closeout Docs | 2026-09-21 | 2026-09-24 | 3 | Project Manager | 0% | ◌ Pending
LEGEND:
| Complete (100%) |  | In Progress |  | Not Started |  | Milestone |  | Current Week
[9 empty] | 46027 | 46034 | 46041 | 46048 | 46055 | 46062 | 46069 | 46076 | 46083 | 46090 | 46097 | 46104 | 46111 | 46118 | 46125 | 46132 | 46139 | 46146 | 46153 | 46160 | 46167 | 46174 | 46181 | 46188 | 46195 | 46202 | 46209 | 46216 | 46223 | 46230 | 46237 | 46244 | 46251 | 46258 | 46265 | 46272 | 46279 | 46286 | 46293 | 46300 | 46307 | 46314 | 46321 | 46328 | 46335 | 46342 | 46349 | 46356 | 46363 | 46370 | 46377 | 46384
Formulas:
Status = IF(G7=1,"✔ Complete",IF(G7>0,"▶ In Progress",IF(AND(ISNUMBER([Start]),[Start]<=TODAY()),"⚠ Overdue","◌ Pending")))