## Excel Project Tracker
Project Tracker
[6 empty] | Planned Dates |  | Planned Duration |  | Actual Dates |  | Actual Duration
Task | Category | Assigned to | Task Description | Status | % Complete | Start | Finish | Hours | Days | Start | Finish | Hours | Days
1 | Category A | Dan | Enter Description | Status 1 | 100% | 2023-01-01 | 2023-02-01 | 184 | 23 | 2023-01-09 | 2023-02-10 | 200 | 25
2 | Category A | Alice | Enter Description | Status 2 | 100% | 2023-02-01 | 2023-04-12 | 408 | 51 | 2023-01-20 | 2023-04-01 | 408 | 51
3 | Category A | Dan | Enter Description | Status 3 | 100% | 2023-03-25 | 2023-05-15 | 288 | 36 | 2023-03-22 | 2023-04-30 | 224 | 28
4 | Category B | Tom | Enter Description | Status 4 | 100% | 2023-02-26 | 2023-05-03 | 384 | 48 | 2023-02-27 | 2023-05-05 | 400 | 50
5 | Category B | Tom | Enter Description | Status 5 | 100% | 2023-04-20 | 2023-05-15 | 144 | 18 | 2023-04-25 | 2023-07-02 | 392 | 49
6 | Category B | Jamie | Enter Description | Status 6 | 100% | 2023-04-28 | 2023-06-25 | 328 | 41 | 2023-04-28 | 2023-06-22 | 320 | 40
7 | Category C | Joan | Enter Description | Status 7 | 100% | 2023-06-10 | 2023-06-21 | 64 | 8 |  |  | 0 | 0
8 | Category C | Joan | Enter Description | Status 4 | 25% | 2023-06-25 | 2023-07-31 | 208 | 26 |  |  | 0 | 0
9 | Category C | Mark | Enter Description | Status 6 | 45% | 2023-07-05 | 2023-08-01 | 160 | 20 |  |  | 0 | 0
10 | Category C | Liz | Enter Description | Status 3 | 85% | 2023-08-10 | 2023-09-21 | 248 | 31 |  |  | 0 | 0
Make beautiful timelines in PowerPoint for important meetings. | [5 empty] | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
Formulas:
Days = NETWORKDAYS([Planned Dates],[Finish])
Days = NETWORKDAYS([Actual Dates],[Finish])
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Trial Edition.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint.
Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce your Project Tracker slide.

## Setup
Setup Project Tracker
Status | Assigned To | Categories
Status 1 | Dan | Category A
Status 2 | Alice | Category B
Status 3 | Tom | Category C
Status 4 | Jamie | Category D
Status 5 | Joan | Category E
Status 6 | Mark | Category F
Status 7 | Liz | Category G
Percent Complete
5%
10%
15%
20%
25%
30%
35%
40%
45%
50%
55%
60%
65%
70%
75%
80%
85%
90%
95%
100%