## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2025
2026
Planning
Acquisition
Implementation
Review and closure
Requirements
Feasibility study
Vendor selection
Infrastructure config
System integration
Data migration
Training & documentation
May
Jul
Sep
Nov
Jan
Mar
May
Jun 10 - Jun 30
Infrastructure assessment
Jun 16 - Jul 6
Stakeholder interviews
Jul 12 - Aug 1
Cost-benefit analysis
Aug 2 - Aug 22
Executive approval
Aug 30 - Sep 13
Identify vendors
Sep 11 - Sep 26
Issue RFP
Sep 30 - Oct 20
Evaluate proposals
Oct 12 - Nov 1
Draft final contracts
Oct 23 - Nov 10
Hardware purchases
Oct 26 - Nov 12
Software license purchases
Nov 20 - Dec 10
Install hardware
Nov 29 - Dec 19
Configure network and security protocols
Dec 18 - Jan 7
Integrate new hardware
Dec 26 - Jan 15
Perfom compatibiilty testing
Jan 2 - Jan 22
Conduct UAT
Jan 23 - Feb 6
Migrate data
Feb 6 - Mar 4
Validate data integrity
Mar 5 - Mar 17
Create training materials
Mar 17 - Mar 29
Conduct training sessions
Mar 17 - Mar 29
Gather feedback
Mar 23 - Apr 4
Complete documentation
Apr 19 - May 1
Handover to IT
Jul
Today
15 days
15 days
15 days
15 days
10 days
12 days
15 days
15 days
13 days
13 days
15 days
15 days
15 days
15 days
15 days
11 days
19 days
9 days
9 days
9 days
10 days
10 days
Project kickoff
May 31
Hardware & software acquisition
Aug 30
Integration & testing
Nov 20
Data migration completed
Mar 5
Project closure
Jul 6
Executive report Gantt chart template