## Project Gantt Chart
Project Gantt Chart Template for Excel
Best for: Project managers tracking tasks, dependencies, and milestones across the full project lifecycle.
Start | 2026-04-06 |  | End | 2026-08-15 |  |  | View | Weekly |  | Gantt View (updates automatically when task dates change)
ID | Task Title | Phase | Start Date | End Date | Duration (days) | % Complete | Dependency | Milestone | Notes | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
1 | Project kickoff | Initiation | 2026-04-06 | 2026-04-06 | 1 | 100% |  | Yes
2 | Requirements gathering | Planning | 2026-04-07 | 2026-04-17 | 11 | 100% | 1 | No
3 | Resource planning | Planning | 2026-04-21 | 2026-04-24 | 4 | 100% |  | No
4 | Scope approval | Planning | 2026-04-20 | 2026-04-20 | 1 | 100% | 2 | Yes
5 | Work breakdown structure | Planning | 2026-04-21 | 2026-04-24 | 4 | 80% | 3 | No
6 | UX/UI design | Design | 2026-04-27 | 2026-05-15 | 19 | 0% | 4 | No | Create wireframes and visuals
7 | Prototype validation | Design | 2026-05-10 | 2026-05-15 | 6 | 0% |  | No
8 | Risk assessment | Planning | 2026-05-04 | 2026-05-08 | 5 | 0% | 4 | No
9 | Project plan baseline | Planning | 2026-05-11 | 2026-05-11 | 1 | 0% |  | Yes | Approve timeline, budget, and resources
10 | Environment setup | Execution | 2026-05-12 | 2026-05-19 | 8 | 0% |  | No
11 | Architecture review | Design | 2026-05-18 | 2026-05-20 | 3 | 0% | 5 | Yes | Validate technical approach
12 | Development sprint 1 | Execution | 2026-05-21 | 2026-06-12 | 23 | 0% | 6 | No | Build core functionality
13 | Data migration prep | Execution | 2026-06-01 | 2026-06-12 | 12 | 0% |  | No
14 | Development sprint 2 | Execution | 2026-06-15 | 2026-07-03 | 19 | 0% | 7 | No | Complete remaining backlog
15 | Test plan sign-off | Testing | 2026-07-01 | 2026-07-01 | 1 | 0% | 9 | Yes
16 | QA testing | Testing | 2026-07-06 | 2026-07-17 | 12 | 0% | 8 | No | Execute test scripts
17 | Training materials | Closure | 2026-07-13 | 2026-07-21 | 9 | 0% |  | No
18 | User acceptance testing | Testing | 2026-07-20 | 2026-07-24 | 5 | 0% |  | No | Validate with stakeholders
19 | Stakeholder training | Closure | 2026-07-22 | 2026-07-24 | 3 | 0% | 18 | No
20 | Launch readiness review | Closure | 2026-07-27 | 2026-07-28 | 2 | 0% |  | Yes
21 | Go-live | Closure | 2026-07-31 | 2026-07-31 | 1 | 0% |  | Yes
22 | Hypercare support | Closure | 2026-08-03 | 2026-08-14 | 12 | 0% |  | No
23 | Project retrostpective | Closure | 2026-08-15 | 2026-08-15 | 1 | 0% |  | Yes
How to use | Edit the blue input cells. The weekly Gantt view updates automatically based on task start and end dates.
Legend | Task bar | Milestone | Formula cell | Input cell | Date check
Note on B3: Automatically calculates the first task start date in the template.
Note on E3: Automatically calculates the latest task end date in the template.
Note on F5: Duration is formula-driven: end date - start date + 1 day.