## Simple Gantt Chart
Simple Gantt Chart Template for Excel
| ID | Task | Start Date | End Date | Duration (days)
| 1 | Project kickoff | 2026-04-01 | 2026-04-01 | 1
| 2 | Market research review | 2026-04-02 | 2026-04-04 | 3
| 3 | Define campaign goals | 2026-04-05 | 2026-04-06 | 2
| 4 | Audience segmentation | 2026-04-07 | 2026-04-09 | 3
| 5 | Messaging framework | 2026-04-10 | 2026-04-12 | 3
| 6 | Content plan | 2026-04-13 | 2026-04-15 | 3
| 7 | Landing page draft | 2026-04-16 | 2026-04-19 | 4
| 8 | Design assets | 2026-04-16 | 2026-04-20 | 5
| 9 | Email campaign setup | 2026-04-21 | 2026-04-23 | 3
| 10 | Social media schedule | 2026-04-21 | 2026-04-24 | 4
| 11 | Ad creatives production | 2026-04-22 | 2026-04-26 | 5
| 12 | Internal review | 2026-04-27 | 2026-04-28 | 2
| 13 | Campaign launch | 2026-04-29 | 2026-04-29 | 1
| 14 | Performance monitoring | 2026-04-30 | 2026-05-06 | 7
| 15 | Campaign wrap‑up report | 2026-05-07 | 2026-05-09 | 3
Instructions: Edit the Start Date or End Date for each task. The Duration and the Gantt chart update automatically.
Tip: Add or remove tasks as needed. If you extend the list, update the Gantt chart's data range (right-click on chart -> Select Data).