## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
Preparation
Audit
performance
Close out
Preparation
step
Kick-off
Phase I
Phase II
Phase III
Consolidation
Jan
Feb
Mar
100%
Review audit contract
100%
Review previous annual audit reports
100%
Assemble audit team and brief
Apr
6
7
8
9
10
11
12
13
14
Kick-off meeting
Finalize access to materials and workspace
Audit of income statements and balance sheet
100%
Develop preliminary questions
100%
Discuss questions with client
100%
Phase I Preliminary findings
Audit of software development operations
100%
Develop preliminary questions
100%
Discuss questions with client
100%
Phase II Preliminary findings
Audit of accounting / financial operations
70%
Develop preliminary questions
60%
Discuss questions with client
Phase III Preliminary findings
Consolidate findings and recommendations
Prepare audit report draft
Deliver final audit report
Complete audit
Mar 24
Start contract
Feb 1
Phase I
Feb 26
Phase II
Mar 2
Phase III
Mar 7
Annual audit project plan
Made with

## Slide 3
Sales process
Kick-off
Engagement
Close out
May
Jun
100%
Refine requirements with customer
100%
Draft and finalize statement of work
100%
Negotiate contract
Jul
Aug
Sep
Oct
05/01
05/24
06/16
07/09
08/01
08/24
09/16
10/09
Kick-off meeting with Engagement team and customer
Finalize engagement schedule, access to resources and reporting scenario
Preliminary interviews
Preliminary recommendations
Follow up interviews
Preliminary findings
Discuss preliminary findings with customer
Follow up research
Discuss preliminary recommendations with customer
Prepare final report
Present final report to customer
Follow up activity
Final documented reports
Engagement complete
First status report
Second status report
Final status report
Sign contract
Consulting Engagement Schedule
Resources
Associate Consultants
Engagement Manager
Practice Director
Sales Executive
Made with

## Slide 4
Research
Today
2022
Q1
Q2
Q3
Q4
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
100%
Baseline current process and procedures
100%
1st process improvement presentation
100%
1st process improvement buy-in meetings
100%
2nd process improvement presentation
40%
2nd process improvement buy-in meetings
3rd process improvement presentation
3rd process improvement buy-in meetings
Implementation plan and schedule
Implementation plan buy-in meetings
Obtain buy-in process improvement plan
Proposal
100%
Initial entrance
Research
40%
100%
0%
Implementation
Made with
Process Improvement Project Schedule