## Excel Critical Path Tracker
| Critical Path Tracker | [10 empty] | - Critical Path |  |  |  |  | - Non Critical Path |  |  |  |  | DIDx - Predecessors' ID | [9 empty] | 0
[16 empty] | x | - Holiday
| PROJECT START DATE |  | 2019-09-01 |  | TODAY DATE | TODAY DATE | 2019-09-07
[9 empty] | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18
| ID* | Items* | Task Duration | DID1* | Start Date | Helper | Finish Date | PERIODS | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23
| 1 | Task 1 | 2 |  | 2019-09-01 | 2019-09-01 | 2019-09-03
| 2 | Task 2 | 1 | 1 |  | 2019-09-04 | 2019-09-05
| 3 | Task 3 | 3 | 2 |  | 2019-09-06 | 2019-09-11
| 4 | Task 4 | 3 | 3 |  | 2019-09-12 | 2019-09-17
| 5 | Task 5 | 4 |  | 2019-09-12 | 2019-09-12 | 2019-09-18
| 6 | Task 6 | 1 | 5 |  | 2019-09-19 | 2019-09-20
| 7 | Task 7 | 2 | 5 |  | 2019-09-19 | 2019-09-23
| 8 | Task 8 | 6 |  | 2019-09-04 | 2019-09-04 | 2019-09-12
| 9 | Task 9 | 2 | 8 |  | 2019-09-13 | 2019-09-17
| 10 | Task 10 | 1 | 5 |  | 2019-09-19 | 2019-09-20
Make beautiful timelines in PowerPoint for important meetings. | [8 empty] | 2019-09-01: Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
C
C
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Trial Edition.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of
PowerPoint. Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce a PowerPoint Gantt chart slide.
Note on G9: If highlighted, enter date

## Holidays
Critical Path Tracker
Holiday every |  | Y/N*
| Sunday | Y
| Monday | N
| Tuesday | N
| Wednesday | N
| Thursday | N
| Friday | N
| Saturday | Y
Holiday on |  | Date (maximum of 40 dates)*
|  | 2009-12-25 | Christmas Day | 2009-12-25
|  | 2010-01-01 | New Year's Day | 2016-01-01
|  | 2010-01-18 | Martin Luther King Day | 2016-01-18
|  | 2010-02-15 | Presidents Day | 2016-02-15
|  | 2010-05-31 | Memorial Day | 2016-05-31
|  | 2010-07-04 | Independence Day | 2016-07-04
|  | 2010-09-06 | Labor Day | 2016-09-06
|  | 2010-10-11 | Columbus Day | 2016-10-11
|  | 2010-11-11 | Veterans' Day | 2016-11-11
|  | 2010-11-25 | Thanksgiving Day | 2016-11-25
|  | 2010-12-25 | Christmas Day