## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2022
2019
MAIN DEV
Design
Oct
2020
Apr
Jul
Oct
2021
Apr
Jul
Oct
2022
Wireframes
Datagrid Mockups
Wireframes
Charting Mockups
Main Dev
Focus on Charting Dev
Hotfix & Feedback
SS Release
Release 3
R4
R5
R6
R7
R8
MSP Release
R9
R10
R11
Onboarding
Today
35 wks
Oct 1 - Jun 1
94 wks
Jun 2 - Mar 22
644.8 days
Oct 1 - Mar 21
53.4 days
Jan 9 - Mar 24
58.1 days
Mar 25 - Jun 15
58 days
Jun 15 - Sep 3
56 days
Sep 5 - Nov 23
57.5 days
Nov 25 - Feb 13
56 days
Feb 14 - May 3
57.4 days
May 4 - Jul 22
71 days
Oct 1 - Jan 7
55 days
Jul 24 - Oct 9
56.7 days
Oct 11 - Dec 28
57.4 days
Dec 30 - Mar 21
17 days
Jan 1 - Jan 23
40 days
Jan 26 - Mar 21
18.9 days
Mar 19 - Apr 14
40 days
Apr 16 - Jun 10
35.2 days
Nov 12 - Dec 31
100%
Nov 16 - Apr 5
Wave 1: Gemstone
100%
Apr 7 - Dec 1
Wave 2: Pebble
50%
Nov 24 - Jul 20
Wave 3: Sand
Jul 19 - Mar 28
Wave 4: Charting
0%
20 wks
34 wks
34 wks
36 wks
Customer Feedback
Customer Feedback
Gemstone
Pebbles
Sand
Product RTW
Mar 2, 2022
Mar 29, 2020
Nov 19, 2020
Jul 16, 2021
Data Grid
Oct 15, 2020
Mar 2
May 21
Roadmap with key Milestones and Sprint Schedule
SaaS Product Development Plan
Architect: Alex
Dev Lead: Tudor
Dev Lead: Bogdan
Design: Narcis
PM: Carmen
Core Dev
Main Dev
Design