## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2020
2020
Today
Jun
Jul
Implementation Kick-Off
Jun 2
Staffing Plan
Jun 16
Testing
Jul 6
Implementation
Jul 30
Final Resource Plan
Jun 11
Development Completed
Jun 28
8 days
Jun 3 - Jun 12
Project Objectives
8 days
Jun 11 - Jun 22
Detailed Reqs.
4 days
Jun 11 - Jun 16
Hardware Reqs.
12 days
Jun 4 - Jun 21
Migration
10 days
Jun 11 - Jun 24
DB Backup
8 days
Jun 17 - Jun 28
Front End Development
5 days
Jun 25 - Jul 1
Mobile Client
14 days
Jun 30 - Jul 18
Prepare Environment
10 days
Jul 18 - Jul 31
System Configuration
Project Planning