## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2021
2021
Today
Day 1
6
11
16
21
26
31
36
41
46
51
56
Jan 27 - Jan 31
3 days
0%
PC Image Analysis
Feb 3 - Feb 10
6 days
0%
PC Image Preparation
Feb 7 - Feb 14
5 days
0%
Smartphone Image Preparation
Feb 17 - Feb 21
3 days
0%
Optimization
Feb 21 - Feb 27
5 days
0%
PC Image Test
Feb 21 - Feb 27
5 days
0%
Smartphone Test
Feb 26 - Mar 6
6 days
0%
PC Image Sign-Off
Feb 28 - Mar 7
5 days
0%
Smartphone Image Sign-Off
Mar 4 - Mar 7
2 days
0%
Documentation
Mar 10 - Mar 12
3 days
0%
Helpdesk Training
Production
Mar 17
Project Approval
Jan 21
Image Rolled Out
Feb 17
Image Approved
Mar 4
Project Hand-Off
Mar 20