## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2022
2023
Today
Jun
Aug
Oct
Dec
Feb
Apr
Jun
2022
2023
6/25 - 7/21
27 days
Requirements
7/5 - 8/8
35 days
Validation
7/25 - 9/1
39 days
Data Analysis
93 days
7/12 - 10/12
Architectural Review
67 days
10/16 - 12/21
System Design
9/7 - 10/14
38 days
Database
9/25 - 10/20
26 days
Data Improve
10/15 - 12/16
63 days
Coding
57 days
10/31 - 12/26
Website Testing
56 days
12/30 - 2/23
Online Testing
1/15 - 4/9
85 days
Coding
3/25 - 4/30
37 days
System Testing
4/1 - 5/27
57 days
Stabilization
77 days
1/29 - 4/15
Performance Enhancing
92 days
4/19 - 7/19
Integration with Website
6/14 - 7/3
20 days
User Acceptance Testing
7/2 - 7/25
24 days
Documentation
7/10 - 7/30
21 days
Stage 1 Submission
Validation
9/24/2022
Minimal Prototype
12/20/2022
Integrated Prototype
4/1/2023
Integration
5/21/2023
Kick-Off
6/18/2022
Submission
7/31/2023