## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2021
2021
Plan
Test
Develop
Launch
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2021
Assemble Resources
Working Plans
Subcontractor Selection
Helpdesk Content Plan
Planning R2 Begin
Performance Validation
Test Complete
Monitoring
Phase Sync
Load Balance
Integration I
Integration II
Integration III
Alpha Build
Prototype
Development Phase I
Development Phase II
RTW Deployment
RC Pilot Deployment
V2 Development Begins
Mon, Nov 1, 2021
WW Launch Event
Beta Blog Launch
July 4, 2021
Gartner Analyst Review
November 1, 2021
Press Release
July 16, 2021
Public Website Live
November 1, 2021
Today
46 days
Jan 1 - Mar 6
38.5 days
Feb 1 - Mar 25
55 days
Mar 1 - May 16
46.5 days
5/17 - 7/20
Aug 1
Feb 10
May 1
Jun 26
Aug 14
Oct 2
36.5 days
May 11 - Jun 30
34.5 days
Jun 30 - Aug 17
33.5 days
Aug 18 - Oct 4
30.5 days
Apr 1 - May 13
23.5 days
Mar 1 - Apr 1
145.5 days
Apr 1 - Oct 21
50.7 days
Aug 11 - Oct 21
Oct 19
Aug 4
57.6 days
Oct 1 - Dec 22
Project Kickoff
Jan 25
Executive Review
Mar 10
Executive Decision
Mar 21
Beta Release
Jun 30
Release Candidate
Oct 1
Final Release
Oct 20
Planning R2 Begin
May 29
Planning R2 Begin
Jun 19
Planning R2 Begin
Jul 10
Product Development Roadmap template