## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2021
2023
Today
Apr
Jul
Oct
2022
Apr
Jul
Oct
2023
Apr
System Design
141 days
5/21 - 11/21
80%
Coding
73 days
11/21 - 3/22
73%
Code Improvements
128 days
3/22 - 8/22
56%
Stabilization
43 days
8/22 - 10/22
20%
Integration with Website
77 days
8/22 - 11/22
15%
User Acceptance
97 days
10/22 - 2/23
Documentation
105 days
1/23 - 5/23
Kick-Off
5/1/21
Minimal Prototype
9/30/21
Submission
11/25/21
Release Web Prototype
3/1/22
Online Testing
5/20/22
Release
3/15/23
Integration
10/30/21
Validation
7/22/22
Exec Review
1/1/23