## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2021
2021
Today
Feb
Mar
Apr
May
Jun
19 days
Feb 12 - Mar 10
Scope
100%
27 days
Feb 15 - Mar 23
Project Resources
76%
17 days
Mar 1 - Mar 23
Analysis
100%
35 days
Mar 23 - May 10
Design
70%
5 days
May 10 - May 16
Draft Specs
37%
18 days
Apr 27 - May 20
Development
40%
24 days
May 9 - Jun 10
Coding
20%
19 days
May 17 - Jun 10
UI
75%
22 days
May 24 - Jun 22
Testing
15%
13 days
Jun 1 - Jun 17
Training
0%
11 days
May 29 - Jun 14
Documentation
10%
Project Sponsor
Feb 15
Analysis Complete
Mar 23
Functional Design Complete
May 10
Project Status Report
Jun 14