## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/office-timeline/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
2022
2023
Revisions
Today
Week 1
6
11
16
21
26
31
Schedule Revision
Sep 10
Schedule Revision
Nov 13
Schedule Revision
Jan 19
1.1 weeks
1.2 weeks
01.27 - 02.03
Mooring & Safety Gear
12.18 - 01.29
5.9 weeks
Machinery & Electrical Installation
10.07 - 11.24
6.8 weeks
Engine Room & Accommodation
09.18 - 10.03
2.2 weeks
Hatch & Superstructure
08.30 - 09.22
3.3 weeks
Steel Profiles
08.05 - 08.31
26 days
Engineering
02.04 - 03.23
6.8 weeks
Outfitting Afloat
12.10 - 12.18
Coating
11.24 - 12.13
2.8 weeks
Block Assembly
Steel Cutting
Aug 28
All Blocks Complete
Nov 25
Navigation Installation Done
Jan 21
Project Kick-Off
Aug 4
Adjusters
Oct 26
Control Systems
Dec 26
Sea Trial 1
Mar 11
Sea Trial 2
Mar 24
Launch
Mar 31
Known Risk 3
Feb 7
Known Risk 4
Mar 11
Known Risk 1
Sep 20
Known Risk 2
Dec 18
Visual Schedule